## YEAR 1-2 ACTIVITIES
MARDS, 2 years project plan
WP, Actions, Deliverables | Titles | RESPONSIBLE PARTNER | INCLUDED PARTNER | STATUS | # WEEKS | MONTHS | [23 empty] | Note/Action
WP1/PRE | Monitoring and analysing of national systems and policies of doctoral education in Montenegro and Albania and comparing with EU practices |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A1.1 | Evaluation of the existing doctoral education policy and standards in Montenegro and Albania and comparing with EU practices | University of Zagreb (University of Vienna) | ALL |  | 16 | bar: MONTHS M2 to MONTHS M5
A1.2 | Organization of a Conference on doctoral education in Montenegro and Albania | University of Zagreb (University of Vienna) | ALL |  | 6 | bar: MONTHS M5 to MONTHS M7
A1.3 | Recommendations and purpose of basic legal documents on university and national levels | University of Zagreb (University of Vienna) | ALL |  | 18 | bar: MONTHS M4 to MONTHS M12
Deliverables | [5 empty] | MONTHS M5: DEV1.1; MONTHS M7: DEV1.2; MONTHS M12: DEV1.3
WP2/DEV | Training of Montenegrin and Albanian academic staff and professionals/administration in doctoral education |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A2.1 | Training of academic and professional staff on EU practices of doctoral education | University of Banska Bystrica (University of Vienna) | ALL |  | 20 | bar: M3 to DEV1.3 M12
A2.2 | Creating a Guidelines and recommendations for WB academics and professionals in doctoral studies | University of Banska Bystrica (University of Vienna) | ALL |  | 4 | bar: DEV1.2 M11 to DEV1.3 M12
Deliverables | [5 empty] | DEV1.3 M18: D2.1_A; DEV1.3 M24: D2.1 ,D2.2
WP3/DEV | Establishing a new model of funding doctoral studies on national levels. |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A3.1 | Evaluation of models for funding doctoral studies in Montenegro and Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL |  | 8 | bar: M5 to M8
A3.2 | Adoption of bylaws on funding doctoral studies in Montenegro | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL |  | 20 | M8: 4X; M9: 2X2=; M10: 4X; M11: 4X; M12: 4X; M13: 2X; M14: 2X; M15: 2X; M16: X=
A3.3 | Adoption of bylaws on funding doctoral studies in Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL |  | 20 | M8: 4X; M9: 2X2=; M10: 4X; M11: 4X; M12: 4X; M13: 2X; M14: 2X; M15: 2X; M16: X=
Deliverables | [5 empty] | D2.1_A M22: D3.1
WP4/DEV | Establishment and start-up of Joint Pilot Doctoral Schools |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A4.1 | Development of the Curricula for joint Doctoral Schools | University of Montenegro (University of Shkodra) | ALL |  | 8 | M11: 2X2=; M12: 2X2=; M13: 4X; M14: 2X2=; M15: 2X; M16: 2X2=; M17: 4X; M18: 2X2=
A4.2 | Equipping the laboratories and other infrastructure at partner universities | University of Montenegro (University of Shkodra) | ALL |  | 24 | bar: M2 to M12
A4.3 | Accreditation of the Doctoral Schools
A4.4 | Enrolling the first generation |  |  |  |  | M18: 4X; M19: 4X; M20: 4X; M21: 4X; D3.1 M22: 2X; D3.1 M23: 2X; D3.1 M24: 2x
Deliverables | [5 empty] | M12: DEV4.3; M18: D4.1 D4.2 D4.3 D4.4; M20: D4.5; D3.1 M24: D4.6
W5/QPLN | Quality plan |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A5.1 | Internal Quality Control | University of Maribor (University of Vienna) | ALL |  | 12 | bar: M2; M4; M6; M8; M10; DEV4.3 M12 to DEV4.3 M14; DEV4.3 M16 to D4.5 M20; D4.5 M22; D4.6 M24
A5.2 | External Quality Control | University of Maribor (University of Vienna) | ALL |  | 10 | bar: M3; M5; M7; M9; M11; DEV4.3 M15; D4.1 D4.2 D4.3 D4.4 M18; D4.5 M21; D4.5 M23 to D4.6 M24
Deliverables | [5 empty] | M3: D5.1; DEV4.3 M13: D5.3
WP6/DISS EXP | Dissemination of the project |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A6.1 | Creation and updating project web site | University of Montenegro, UDG, under help of Metropolitan University Tirana and PRIDE network | ALL |  | 12 | bar: M1 to D5.3 M24
A6.2 | Creating and distribution of dissemination documents | University of Montenegro, UDG, under help of Metropolitan University Tirana and PRIDE network | ALL |  | 6 | bar: M2; D5.1 M4; D5.1 M6; D5.1 M8 to D5.3 M13; D5.3 M15; D5.3 M17; D5.3 M19; D5.3 M21; D5.3 M23 to D5.3 M24
A6.3 | Organizing dissemination conference with stakeholders | bar: D5.3 M20
Deliverables | [5 empty] | D5.1 M6: D6.1 D6.2 D6.3; D5.1 M12: D6.1 D6.2; D5.3 M18: D6.1 D6.2 D6.3
WP7/DISS/EXP | Explotation and Sustainability of the project results |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A7.1 | Regular meetings about MARDS flow with stakeholders | Metropolitan University Tirana, Polytechnic Univerist of Tirana, Vlore Uni (under help of all) | ALL |  | 6 | bar: M2; M4; D6.1 D6.2 D6.3 M6; D6.1 D6.2 D6.3 M8; D6.1 D6.2 D6.3 M11 to D6.1 D6.2 D6.3 M24
A7.2 | Universities – stakeholders networking in Montenegro and Albania | Polytechnic University Tirana (under help of all) | ALL |  | 6 | bar: M4; D6.1 D6.2 D6.3 M6; D6.1 D6.2 D6.3 M8; D6.1 D6.2 D6.3 M11 to D6.1 D6.2 M12; D6.1 D6.2 M16 to D6.1 D6.2 D6.3 M24
A7.3 | Establishment of sustainable scholarships in Albania and Montenegro | bar: D6.1 D6.2 M13 to D6.1 D6.2 M15
A7.4 | Promotion of Doctoral School in Region | bar: D6.1 D6.2 M16 to D6.1 D6.2 D6.3 M20
Deliverables | [5 empty] | M4: D7.1; D6.1 D6.2 M12: D6.3; D6.1 D6.2 D6.3 M18: D6.3
WP8/DISS/EXP | Management of the project |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A8.1 | Daily management of the project | University of Montenegro | ALL |  | 24 | bar: M1 to D6.3 M24
A8.2 | Precise guidelines for management of the project | University of Montenegro | ALL |  | 4 | bar: M1 to M2
A8.3 | Regular meetings of project bodies | University of Montenegro | ALL |  | 3 | bar: M2; D7.1 M7; D6.3 M12 to D6.3 M13; D6.3 M19; D6.3 M24
[8 empty] | D8.1 |  |  | D8.1 |  |  | D8.1 |  |  | D8.1 |  |  | D8.1 |  |  | D8.1
[7 empty] | D8.2 |  |  |  |  | D8.2 |  |  |  |  | D8.2 | [5 empty] | D8.3
Note on K7: Radovan Stojanovic: DE1.1 "Report on the “state of the art” in doctoral education in Montenegro and Albania and comparison with EU practices" Report M5 "University of Zagreb (University of Vienna)"
Note on M7: Radovan Stojanovic: DE1.2 "Proceedings from conference about doctoral education in Montenegro and Albania" "Report, Product" M7 "University of Zagreb (University of Vienna)"
Note on R7: Radovan Stojanovic: DE1.3 "Legal documents to be send to responsible bodies for adopting" Report M12
Note on X11: Radovan Stojanovic: DE2.1_A "Info on academic and professional training of WB staff/professionals/administrative' at EU" Report M18
Note on AD11: Radovan Stojanovic: D2.1 Report on academic and professional training of WB staff/professionals/administrative' at EU D2.2 Guidelines and recommendations for WB academics and professionals in doctoral studies
Note on AB16: Radovan Stojanovic: Report on appropriate funding doctoral studies in Montenegro and Albania
Note on R22: Radovan Stojanovic: DE4.3 The report on MARDS’s equipment resources Report M12 "Univershity Shkoder and University of Montenegro other Albanian Unis"
Note on X22: Radovan Stojanovic: DE4.1 Curricula book for Joint School suited in Albania (Shkoder) "Teaching, Learning and Training material" M18 "Univershity Shkoder and University of Montenegro" DE4.2 Curricula book for Joint pilot school in Montenegro "Teaching, Learning and Training material" M18 "Univershity Shkoder and University of Montenegro" DE4.4 Final version of accreditation application Report M18 "Univershity Shkoder and University of Montenegro other Albanian Unis"
Note on Z22: Radovan Stojanovic: Decisions on accreditation
Note on AD22: Radovan Stojanovic: The list of the enroled studenst
Note on I26: Radovan Stojanovic: DE5.1 Quality Plan adopted "Report Service" M3
Note on S26: Radovan Stojanovic: DE5.3 Tender for subtracting external QC experts completed Service M13
Note on L31: Radovan Stojanovic: DE6.1 Setting up and maintaining the project web site Product "M1-M36 Every 6 months will be checked this deliverables" DE6.2 Dissemination material created and distributed Product "M1-M36 Every 6 months will be checked this deliverables" DE6.3 Dissemination events with relevant stakeholders organised Events M6, M18, M24 Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
Note on R31: Radovan Stojanovic: DE6.1 Setting up and maintaining the project web site Product "M1-M36 Every 6 months will be checked this deliverables" DE6.2 Dissemination material created and distributed Product "M1-M36 Every 6 months will be checked this deliverables"
Note on X31: Radovan Stojanovic: DE6.1 Setting up and maintaining the project web site Product "M1-M36 Every 6 months will be checked this deliverables" DE6.2 Dissemination material created and distributed Product "M1-M36 Every 6 months will be checked this deliverables" DE6.3 Dissemination events with relevant stakeholders organised Events M6, M18, M24 Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
Note on J37: Radovan Stojanovic: DE7.1 Sustainability strategy adopted Document M4
Note on R37: Radovan Stojanovic: The dissemination events with stakeholders
Note on X37: Radovan Stojanovic: The dissemination events with industry stakeholders
Note on I42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on L42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on O42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on R42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on U42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on X42: Radovan Stojanovic: DE8.1 Overall project management All outputs "M1-M36 Every 3 months will be checked this deliverables"
Note on H43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on M43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on R43: Radovan Stojanovic: DE8.2 Project coordination meetings Events "M1-M36 Deliverable valid for sheduled meetings"
Note on X43: Radovan Stojanovic: DE8.3 Periodical report

## DELIVERABLES
MARDS 's main delievrables (36) Months |  |  | blue: M25-M36 yellow: M18-M24
Delivarable # |  | Type | Month | Responsible | Expected Date
DE1.1 | Report on the “state of the art” in doctoral education in Montenegro and Albania and comparison with EU practices | Report | M5 | University of Zagreb (University of Vienna)
DE1.2 | Proceedings from conference about doctoral education in Montenegro and Albania | Report, Product | M7 | University of Zagreb (University of Vienna)
DE1.3 | Legal documents to be send to responsible bodies for adopting | Report | M12 | All
DE2.1_A | Info on academic and professional training of WB staff/professionals/administrative' at EU | Report | M18 | University of Banska Bystrica (University of Vienna)
DE2.1_B | Report on academic and professional training of WB staff/professionals/administrative' at EU | Report | M24 | University of Banska Bystrica (University of Vienna)
DE2.2 | Guidelines and recommendations for WB academics and professionals in doctoral studies | Teaching and training material | M24 | University of Banska Bystrica (University of Vienna)
DE3.1 | Report on appropriate funding doctoral studies in Montenegro and Albania | Report | M21 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Montenegro | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Albania | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
DE4.1 | Curricula book for Joint School suited in Albania (Shkoder) | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro
DE4.2 | Curricula book for Joint pilot school in Montenegro | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro
DE4.3 | The report on MARDS’s equipment resources | Report | M12 | Univershity Shkoder and University of Montenegro other Albanian Unis
DE4.4 | Final version of accreditation application | Report | M18 | Univershity Shkoder and University of Montenegro other Albanian Unis
DE4.5 | Decisions on accreditation | Decission | M20 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences).
DE4.6 | The list of enrolled students | List | M24 | University of Montenegro
DE5.1 | Quality Plan adopted | Report Service | M3 | University of Maribor University of Vienna
DE5.2 | Internal quality assurance reports delivered | Report | M36 | University of Maribor University of Vienna
DE5.3 | Tender for subtracting external QC experts completed | Service | M13 | University of Maribor University of Vienna
DE5.4 | External quality control and monitoring delivered | Report | M36 | External Experts
DE6.1 | Setting up and maintaining the project web site | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.2 | Dissemination material created and distributed | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.3 | Dissemination events with relevant stakeholders organised | Events | M6, M18, M24 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.4 | MARDS doctorial Colloquium organised | Event | M35 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE7.1 | Sustainability strategy adopted | Document | M4 | Metropolitan University Tirana (under help of UoM)
DE7.2 | University – Stakeholders network created | Product Servise | M36 | Metropolitan University Tirana (under help of UoM)
DE7.3 | Doctoral scholarships provided | Product | M23 | Metropolitan University Tirana (under help of UoM)
DE8.1 | Overall project management | All outputs | M1-M36 Every 3 months will be checked this deliverables | University of Montenegro
DE8.2 | Project coordination meetings | Events | M1-M36 Deliverable valid for sheduled meetings | University of Montenegro
DE8.3 | Periodical and Final reports | Reports | M18, M36 | University of Montenegro